## Instructions
Change Impact Matrix
What is a Change Impact Matrix?
• A descriptive template that captures the details of what is going to change for everyone involved in a project
• A tool that helps the project team prepare for change and allows those impacted to adjust
• A matrix useful for presenting the project context to upper management as it graphically depicts the drivers behind many of the program steps
Which Business Problems Does the Tool Solve?
• Preparing people for change is often the most difficult part of any initiative
• The tool quickly targets the roles that planned changes to process, hierarchy and technology will affect
• Helps project managers wear the dual hats of program manager and change manager
Benefits:
• Provides an at-a-glance understanding of high/medium/low change impacts
• Serves as a discussion guide for planning risk-mitigation activities
• Informs project leaders about areas requiring greater and lesser degrees of communication and training
• Informs those impacted about the degree of impact in advance of change
How to Apply the Tool:
• First column identifies the individual or stakeholder group that will be affected by changes
• Second and third columns describe the specific technology and process changes that will occur
• Four columns on the right indicate the magnitude of the impact of the changes on a given individual or group in four areas
• First, identify a business model change that will impact your organization
• Then, make a list of affected individuals and stakeholder groups
• Assign someone as the owner of each stakeholder group to complete the Change Impact Matrix
• Develop criteria to define high/medium/low change impact status
• Each owner completes the template
• Each owner suggests risk-mitigation activities for high and medium areas
How to Use the results:
• ROLE - Based on how significantly the change impacts the role, adjust the intensity and duration of training/change management assistance
• PROCESS - Based on the degree of process change (and where the change takes place) target the training to address the biggest PROCESS change areas. Consider interactive worksessions with process mapping to help the impacted prepare for the change
• CULTURE - For areas where there are large CULTURAL gaps, use human centered change mechanisms that align values and behaviors. Consider involving Top Management in the change process.
• TECHNOLOGY - For areas where there are large TECHNOLOGY changes, leverage technology partners to perform specific skills training. Consider using simulators, outside exercises, and laboratories to complement the partner's training.

## Change Impact Matrix
Change Impact Matrix
Change Impact Matrix - CRM Implementation Example
Role / Stakeholder Group | Technology | Processes | Role | Process | Culture | Tech
IT Support | Implementation of new CRM Systems and Processes | Supporting the Sales & Support teams use of the new CRM System | Medium | High | Low | Low
Customer Support Teams | Implementation of new CRM Systems and Processes | New reporting, queue mgmt, SLAs, new KPI, new tools, create new reporting | High | Medium | High | High
Sales Management | New CRM System | Supporting Salespeople, reporting changes | Low | Low | Medium | Medium
Individual Salespeople | New CRM System | New methods for sales lead tracking | High | High | Medium | High
How to Apply the Tool:
• First column identifies the individual or stakeholder group that will be affected by changes • Second and third columns describe the specific technology and process changes that will occur • Four columns on the right indicate the magnitude of the impact of the changes on a given individual or group in four areas • First, identify a business model change that will impact your organization • Then, make a list of affected individuals and stakeholder groups • Assign someone as the owner of each stakeholder group to complete the Change Impact Matrix • Develop criteria to define high/medium/low change impact status • Each owner completes the template • Each owner suggests risk-mitigation activities for high and medium areas

## Graphics
Change Impact Matrix - CRM Implementation Example
Role / Stakeholder Group | Technology | Processes | Role | Process | Culture | Tech
IT Support | Implementation of new CRM Systems and Processes | Supporting the Sales & Support teams use of the new CRM System | Medium | High | Low | Low
Customer Support Teams | Implementation of new CRM Systems and Processes | New reporting, queue mgmt, SLAs, new KPI, new tools, create new reporting | High | Medium | High | High
Sales Management | New CRM System | Supporting Salespeople, reporting changes | Low | Low | Medium | Medium
Individual Salespeople | New CRM System | New methods for sales lead tracking | High | High | Medium | High