## Instructions
What is a Circle Dot Chart?
• A set of connected circles in a matrix framework that identifies key deliverables on the horizontal axis and key roles or key individuals on the vertical axis.
• Consists of lines that represent tasks, and circles at the intersection of tasks and functional responsibilities.
• Open circles indicate that an individual function is involved, while solid circles represent the directly responsible individual (DRI) for a given deliverable.
Which Business Problems Does the Tool Solve?
• Besides unclear requirements, unclear responsibilities are one of the leading causes of program delays.
• Providing the team with a crisp picture of key deliverables tied to key functions greatly reduces this problem.
Benefits:
• Provides a clear visual representation of roles and responsibilities
• Helps prevent missed deliverables by clarifying who does what
• Prevents wasted effort resulting from having two people working on the same task
• Helps the team share common understanding of roles at the beginning of the project
How to Apply the Tool:
• The project manager fills out a rough draft of the chart.
• She then holds a review session with the team.
• The team identifies key tasks (approximately 5-15) from the project plan and puts them in time sequence across the top of the chart.
• The team lists the key functions responsible for delivering the program. It is important that participation in a task is discerned from responsibility for delivering the task.
• Indicate any functional group involved in a particular task with an open circle. Represent the one function that is ultimately responsible for fulfilling the task with a solid circle.
• All tasks must have one, and only one, directly responsible individual (DRI)

## Application of Circle Dot
How to Apply the Tool:
• The project manager fills out a rough draft of the chart.
• She then holds a review session with the team.
• The team identifies key tasks (approximately 5-15) from the project plan and puts them in time sequence across the top of the chart.
• The team lists the key functions responsible for delivering the program. It is important that participation in a task is discerned from responsibility for delivering the task.
• Indicate any functional group involved in a particular task with an open circle. Represent the one function that is ultimately responsible for fulfilling the task with a solid circle.
• All tasks must have one, and only one, directly responsible individual (DRI)
• The team should review the Circle Dot Chart early in the program.
• At the end of the review session, the functional representatives sign off on their various assignments.
• Store this document in the project team repository for easy access and review. the chart to reflect these changes.
• When key tasks are coming due, you can quickly review who is responsible for delivering them.

## Circle Dot Template
| Requirements | Vendor Selection | Detailed Requirements | Design Finished | Coding Finished | Alpha Testing
Business Analyst
Business Process Owner
Business Process User
Change Manager
Finance
Project Manager
Quality
Sales
Technical Lead
Training Lead
Vendor